## Sheet1
Defect ID | Detected in Cycle | Build Sequence | Test Phase | Detected in Release | Detected on Date | Detected By | Assigned To | Actual Fix Time (Hrs) | Business/Functionality | Closing Date | Description | Environment | Modified | Priority | Reason Code | Reproducible | Request Type | Severity | Status | Summary
1 | Cycle 1 | UN_01 | System Testing | Release 1 | 07-09-2021 | Ruhi Morajkar |  | 4 | UniformStore_User_ForgotPassword | 08-09-2021 | Email cannot be generated to update the password | QA | 07-09-2021 10:30 | 1-High | Coding Errors | Y | Defect | 1-High |  | If User forgets the password, the email does not reach to update the password.
2 | Cycle 1 | UN_02 | System Testing | Release 1 | 07-09-2021 | Saanya Dhir |  | 4 | UniformStore_Admin_AddProduct | 08-09-2021 | The newly added products are not visible on the website. | QA | 2021-09-07 11:15 | 1-High | Coding Errors | Y | Defect | 1-High |  | When admin adds new products, they are not visible on the website.
3 | Cycle 1 | UN_03 | System Testing | Release 1 | 07-09-2021 | Shravya B C |  | 4 | Uniformstore_admin_Reports_sales_orders | 08-09-2021 | Start Date and End Date cannot be blank | QA | 2021-09-07 11:42 | 1-High | Coding Errors | Y | Defect | 1-High |  | In orders if admin don't want to filter on the basis of dates,still dates get selected.
4 | Cycle 1 | UN_04 | System Testing | Release 1 | 07-09-2021 | Soumya Hugar |  | 4 | UN_20 | 08-09-2021 | No interface to edit and update IP address | QA | 07-09-2021 10:30 | 1-High | Coding Errors | Y | Defect | 1-High |  | If admin is trying to update Customer details, then there are interface to edit IP address Field ,but during searching the particular customer,there’s a field IP address for search.
5 | Cycle 1 | UN_05 | System Testing | Release 1 | 07-09-2021 | Soumya Hugar |  | 4 | UN_5 | 08-09-2021 | Custom fields Section is in appropriate | QA | 2021-09-07 10:45 | 1-High | Coding Errors | Y | Defect | 1-High |  | During addition of Custom fields, one mandatory field “Custom Field Value Name” , once given the field name and edited, value name is not updated, That is, field value name has no functionalities but it is mandatory
6 | Cycle 1 | UN_06 | System Testing | Release 1 | 07-09-2021 | Soumya Hugar |  | 4 | UN_5 | 08-09-2021 | Sort order under custom field is inappropriate | QA | 07-09-2021 10:50 | 1-High | Coding Errors | Y | Defect | 1-High |  | In Custom fields Section, during addition of new custom fields, when new sort order is edited, by default the sort order is displayed as zero, that is no updation in sort order
7 | Cycle 1 | UN_07 | System Testing | Release 1 | 07-09-2021 | Sindhuja pula |  | 4 | UniformStore_AddNewOrder | 08-09-2021 | New Order is added successfully to the system even if all the necessary information is not given and does not make any difference regarding features of the Order. |  | 2021-09-07 11:30 | 1-Critical | Coding Errors | Y | Defect | 1-Medium |  | Before adding a Order to the system ,enough data is not provided and provided details does not reflect any changes to the qualities of order.
8 | Cycle 2 | UN_08 | System Testing | Release 1 | 07-09-2021 | Sindhuja pula |  | 4 | UniformStore_AddNewOrder | 08-09-2021 | Shipping address has to be applied for add on order |  | 2021-09-07 11:30 | 1- Critical | Coding Errors | Y | Defect | 1-Medium |  | For an adding an order,address has to be given
9 | Cycle 1 | UN_09 | System Testing | Release 1 | 07-09-2021 | Sindhuja pula |  | 4 | UniformStore_Delete Existing Order | 08-09-2021 | Existing order has to be deleted by giving order details |  | 2021-09-07 11:30 | 1-Critical | Coding Errors | Y | Defect | 1-Medium |  | Before deleting a Order to the system ,enough data is not provided and details are not given and does not reflect any changes to the qualities of order.
10 | Cycle 2 | UN_10 | System Testing | Release 1 | 07-09-2021 | Sindhuja pula |  | 4 | UniformStore_Delete Existing Order | 08-09-2021 | Recurring ID has to be applied for delete on order |  | 2021-09-07 11:30 | 1- Critical | Coding Errors | Y | Defect | 1-Medium |  | For an Delete an order,Recurring Id has to be given for the existing order and it has not provided.
11 | Cycle 1 | UN_11 | System Testing | Release 1 | 07-09-2021 | Sindhuja pula |  | 4 | UniformStore_Update Order | 08-09-2021 | Existing order has to be update by giving order details by using Order ID |  | 2021-09-07 11:30 | 1-Critical | Coding Errors | Y | Defect | 1-Medium |  | Before Updating a Order to the system ,enough data is not provided and Order ID is not given and does not reflect any changes to the order.
12 | Cycle 1 | UN_12 | System Testing | Release 1 | 07-09-2021 | Rohini |  | 4 | UniformStore_AddNewManufacturer | 08-09-2021 | New Manufacturer is added successfully to the system even if all the necessary information is not given and does not make any difference regarding features of the Manufacturer. | QA | 2021-09-07 11:30 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Before adding a manufacturer to the system ,enough data is not provided and provided details does not reflect any changes to the qualities of manufacturer.
13 | Cycle 1 | UN_13 | System Testing | Release 1 | 07-09-2021 | Rohini |  | 4 | UniformStore_AddNewManufacturer | 08-09-2021 | Repeated addition of manufacturer is allowed with incompletely filled details | QA | 2021-09-07 11:30 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Duplication of manufacturer is possible when SEO URL field is not filled.
14 | Cycle 1 | UN_14 | System Testing | Release 1 | 07-09-2021 | Rohini |  | 4 | UniformStore_AddNewManufacturer | 08-09-2021 | Sort order field does not really order the list as provided | QA | 2021-09-07 11:30 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Sorting doesn’t take place even after specifying the sort order.
15 | Cycle 1 | UN_15 | System Testing | Release 1 | 07-09-2021 | Rohini |  | 4 | UniformStore_UpdateManufacturerDetails | 08-09-2021 | New Manufacturer is added successfully to the system even if all the necessary information is not given and does not make any difference regarding features of the Manufacturer. | QA | 2021-09-07 11:30 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Before updating a manufacturer to the system ,enough data is not provided and provided details does not reflect any changes to the qualities of manufacturer.
16 | Cycle 1 | UN_16 | System Testing | Release 1 | 07-09-2021 | Rohini |  | 4 | UniformStore_UpdateManufacturerDetails | 08-09-2021 | Repeated addition of manufacturer is allowed with incompletely filled details | QA | 2021-09-07 12:23 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Duplication of manufacturer is possible when SEO URL field is not filled while updating.
17 | Cycle 1 | UN_17 | System Testing | Release 1 | 07-09-2021 | Rohini |  | 4 | UniformStore_UpdateManufacturerDetails | 08-09-2021 | Sort order field does not really order the list as provided | QA | 2021-09-07 12:27 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Sorting doesn’t take place even after specifying the sort order.
18 | Cycle 1 | UN_18 | System Testing | Release 1 | 07-09-2021 | Sivaranjani |  | 2 | UN_AddOption | 08-09-2021 | Option value name is inappropriate | QA | 2021-09-07 11:30 | High | Coding Errors | Y | Defect | High | Closed | once the new Options are added to the lists, the Option name is visible whereas the value name is not as it is a required field
19 | Cycle 1 | UN_19 | System Testing | Release 1 | 07-09-2021 | Sivaranjani |  | 2 | UN_AddOption | 08-09-2021 | Sort Order under Option values is not suitable | QA | 2021-09-07 11:30 | High | Coding Errors | Y | Defect | High | Closed | During the addition of new Options, there are 2 Sort order fields to be filled,