## Sheet1
Defect ID | Detected in Cycle | Build Sequence | Test Phase | Detected in Release | Detected on Date | Detected By | Assigned To | Actual Fix Time (Hrs) | Business/Functionality | Closing Date | Description | Environment | Modified | Priority | Reason Code | Reproducible | Request Type | Severity | Status | Summary
1 | Cycle 1 | UN_01 | System Testing | Release 1 | 2021-07-09 | Ruhi Morajkar |  | 1 | UniformStore_User_ForgotPassword
2 | Cycle 1 | UN_02 | System Testing | Release 1 | 2021-07-09 | Saanya Dhir |  | 1 | UniformStore_Admin_AddProduct |  | Email cannot be generated to update the password | QA | 2021-07-09 10:30 | 1-High | Coding Errors | Y | Defect | 1-High |  | If User forgets the password, the email does not reach to update the password.
3 | Cycle 1 | UN_03 | System Testing | Release 1 | 2021-07-09 | Shravya B C |  | 1 | Uniformstore_admin_Reports_sales_orders |  | Size options for clothes not available. | QA | 2021-07-08 16:30 | 1-High | Coding Errors | Y | Defect | 1-High |  | There is no dropdown menu available for choosing sizes of clothes, instead there is an input box for entering size, which accepts any sort of value (number or alphabet).
4 | Cycle 1 | UN_04 | System Testing | Release 1 | 2021-07-09 | Soumya Hugar |  | 1 | Uinformstore_admin_Customer_Ipadrress |  | Order status is showing canceled by default. | QA | 2021-07-08 16:30 | 1-High | Coding Errors | Y | Defect | 1-High |  | After placing order, when user checks the order status, it is by default canceled.
5 | Cycle 1 | UN_05 | System Testing | Release 1 | 2021-07-09 | Soumya Hugar |  | 1 | UniformStore_admin_Customer_CustomField |  | No mails are being received for any functionality. | QA | 2021-07-08 16:30 | 1-High | Coding Errors | Y | Defect | 1-High |  | No emails are being sent for the updation of any information.
6 | Cycle 1 | UN_06 | System Testing | Release 1 | 2021-07-09 | Soumya Hugar |  | 1 | UniformStore_admin_customer_Customfield_sortorder | 2021-08-09 | Company name should be mandatory | QA | 2021-07-08 05:00 | 1-Medium | Coding | Y | Defect | 1-medium |  | While adding company name, the company name field should be made mandatory.
7 | Cycle 1 | UN_07 | System Testing | Release 1 | 2021-07-09 | Sindhuja pula |  | 1 | UniformStore_AddNewOrder | 2021-08-09 | The Quantity field should be mandatory | QA | 2021-07-08 05:00 | 1-Medium | Coding | Y | Defect | 1-medium |  | While placing an order, the quantity filed should be made mandatory.
8 | Cycle 2 | UN_08 | System Testing | Release 1 | 2021-07-09 | Sindhuja pula |  | 1 | UniformStore_AddNewOrder |  | No filter options available. | QA | 2021-07-08 16:30 | 1-High | Coding Errors | Y | Defect | 1-High |  | There is no option for filtering/searching products on the website.
9 | Cycle 1 | UN_09 | System Testing | Release 1 | 2021-07-09 | Sindhuja pula |  | 1 | UniformStore_Delete Existing Order |  | User not being directed to website directly on login. | QA | 2021-07-08 16:30 | 1-High | Coding Errors | Y | Defect | 1-High |  | Whenever the user logins, he is directed to My Accounts page, instead of the main website homepage.
10 | Cycle 2 | UN_10 | System Testing | Release 1 | 2021-07-09 | Sindhuja pula |  | 1 | UniformStore_Delete Existing Order | 2021-08-09 | Price field not mandatory. | QA | 2021-07-09 17:00 | 1-Medium | Coding Errors | Y | Defect | 1-Medium |  | While adding a new product, price field is not mandatory.
11 | Cycle 1 | UN_11 | System Testing | Release 1 | 2021-07-09 | Sindhuja pula |  | 1 | UniformStore_Update Order | 2021-08-09 | Quantity field not mandatory. | QA | 2021-07-09 17:00 | 1-Medium | Coding Errors | Y | Defect | 1-Medium |  | While adding a new product, quantity field is not mandatory.
12 | Cycle 1 | UN_12 | System Testing | Release 1 | 2021-07-09 | Rohini |  | 1 | UniformStore_AddNewManufacturer | 2021-08-09 | Manufacturer field not mandatory. | QA | 2021-07-09 17:00 | 1-Medium | Coding Errors | Y | Defect | 1-Medium |  | While adding a new product, manufacturer details are not mandatory.
13 | Cycle 1 | UN_13 | System Testing | Release 1 | 2021-07-09 | Rohini |  | 4 | UniformStore_AddNewManufacturer | 2021-08-09 | No interface to edit and update IP address | QA | 2021-07-09 10:30 | 1-High | Coding Errors | Y | Defect | 1-High |  | If admin is trying to update Customer details, then there are interface to edit IP address Field ,but during searching the particular customer,there’s a field IP address for search.
14 | Cycle 1 | UN_14 | System Testing | Release 1 | 2021-07-09 | Rohini |  | 4 | UniformStore_AddNewManufacturer | 2021-08-09 | Custom fields Section is in appropriate | QA | 44386.7299 | 1High | Coding Errors | Y | Defect | 1-High |  | During addition of Custom fields, one mandatory field “Custom Field Value Name” , once given the field name and edited, value name is not updated, That is, field value name has no functionalities but it is mandatory
15 | Cycle 1 | UN_15 | System Testing | Release 1 | 2021-07-09 | Rohini |  | 4 | UniformStore_UpdateManufacturerDetails | 2021-08-09 | Sort order under custom field is inappropriate | QA | 2021-07-09 10:50 | 1-High | Coding Errors | Y | Defect | 1-High |  | In Custom fields Section, during addition of new custom fields, when new sort order is edited, by default the sort order is displayed as zero, that is no updation in sort order
16 | Cycle 1 | UN_16 | System Testing | Release 1 | 2021-07-09 | Rohini |  | 4 | UniformStore_UpdateManufacturerDetails |  | Two Unused fields in Customer lists | QA | 2021-07-09 05:48 | 1-medium | UI Error | Y | Defect | 1-medium |  | There are two unused fields in customer list section , no information about those, except icon.
17 | Cycle 1 | UN_17 | System Testing | Release 1 | 2021-07-09 | Rohini |  | 4 | UniformStore_UpdateManufacturerDetails |  | Shipping address has to be applied for add on order | QA | 2021-07-09 11:30 | 1- Critical | Coding Errors | Y | Defect | 1-Medium |  | For an adding an order,address has to be given
18 | Cycle 1 | UN_18 | System Testing | Release 1 | 2021-07-09 | Sivaranjani |  | 2 | UniformStore_AddOption |  | Repeated addition of manufacturer is allowed with incompletely filled details | QA | 2021-07-09 11:30 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Duplication of manufacturer is possible when SEO URL field is not filled.
19 | Cycle 1 | UN_19 | System Testing | Release 1 | 2021-07-09 | Sivaranjani |  | 2 | UniformStore_AddOption |  | Sort order field does not really order the list as provided | QA | 2021-07-09 11:30 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Sorting doesn’t take place even after specifying the sort order.
[11 empty] | Repeated addition of manufacturer is allowed with incompletely filled details | QA | 2021-07-09 12:23 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Duplication of manufacturer is possible when SEO URL field is not filled while updating.
[11 empty] | Sort order field does not really order the list as provided | QA | 2021-07-09 12:27 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Sorting doesn’t take place even after specifying the sort order.
[11 empty] | SEO URL field should be mandatory as it holds the unique value with respect to manufacturer identity. | QA | 2021-07-09 10:56 | 3-Medium | Coding Errors | Y | Defect | 3-Medium |  | SEO URL field should be made mandatory.

## Sheet3
Row Labels | Count of Severity
1-Critical | 5 | 1-Critical | 5
1-High | 13 | 1-High | 13
1-medium | 16 | 1-medium | 16
3-Medium | 3 | 3-Medium | 3
High | 2 | High | 2
medium | 2 | medium | 2
(blank) |  | (blank)
Grand Total | 41 | Grand Total | 41
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Sheet5
Row Labels | Count of Priority
1- Critical | 2
1-Critical | 6
1-High | 13
1-Medium | 11
3-Medium | 3
High | 2
Medium | 2
(blank)
Grand Total | 39

## Sheet2
Defect ID | Detected in Cycle | Build Sequence | Test Phase | Detected in Release | Detected on Date | Detected By | Assigned To | Actual Fix Time (Hrs) | Business/Functionality | Closing Date | Description | Environment | Modified | Priority | Reason Code | Reproducible | Request Type | Severity | Status | Summary
1 | Cycle 1 | UN_01 | System Testing | Release 1 | 2021-07-09 | Ruhi Morajkar |  | 1 | UniformStore_User_ForgotPassword |  | Email cannot be generated to update the password | QA | 2021-07-09 10:30 | 1-High | Coding Errors | Y | Defect | 1-High |  | If User forgets the password, the email does not reach to update the password.
2 | Cycle 1 | UN_02 | System Testing | Release 1 | 2021-07-09 | Ruhi Morajkar |  | 1 | UniformStore_User |  | Size options for clothes not available. | QA | 2021-07-08 16:30 | 1-High | Coding Errors | Y | Defect | 1-High |  | There is no dropdown menu available for choosing sizes of clothes, instead there is an input box for entering size, which accepts any sort of value (number or alphabet).
3 | Cycle 1 | UN_03 | System Testing | Release 1 | 2021-07-09 | Ruhi Morajkar |  | 2 | UniformStore_User |  | Order status is showing canceled by default. | QA | 2021-07-08 16:30 | 1-High | Coding Errors | Y | Defect | 1-High |  | After placing order, when user checks the order status, it is by default canceled.
4 | Cycle 1 | UN_04 | System Testing | Release 1 | 2021-07-09 | Ruhi Morajkar |  | 2 | UniformStore_User |  | No mails are being received for any functionality. | QA | 2021-07-08 16:30 | 1-High | Coding Errors | Y | Defect | 1-High |  | No emails are being sent for the updation of any information.
5 | Cycle 2 | UN_05 | System Testing | Release 1 | 2010-07-08 | Ruhi Morajkar |  | 2 | UniformStore_User_Registration |  | Company name should be mandatory | QA | 2021-07-08 05:00 | 1-Medium | Coding | Y | Defect | 1-medium |  | While adding company name, the company name field should be made mandatory.
6 | Cycle 2 | UN_06 | System Testing | Release 1 | 2010-07-08 | Ruhi Morajkar |  | 2 | UniformStore_User_Purchase |  | The Quantity field should be mandatory | QA | 2021-07-08 05:00 | 1-Medium | Coding | Y | Defect | 1-medium |  | While placing an order, the quantity filed should be made mandatory.
7 | Cycle 1 | UN_07 | System Testing | Release 1 | 2021-07-09 | Saanya Dhir |  | 1 | UniformStore_Admin_AddProduct |  | The newly added products are not visible on the website. | QA | 2021-07-09 11:15 | 1-High | Coding Errors | Y | Defect | 1-High |  | When admin adds new products, they are not visible on the website.
8 | Cycle 1 | UN_08 | System Testing | Release 1 | 2021-07-09 | Saanya Dhir |  | 2 | UniformStore_User |  | No categories of products is visible. | QA | 2021-07-08 16:30 | 1-High | Coding Errors | Y | Defect | 1-High |  | Customers are not able to view all the products category-wise.
9 | Cycle 1 | UN_09 | System Testing | Release 1 | 2021-07-09 | Saanya Dhir |  | 2 | UniformStore_User |  | No filter options available. | QA | 2021-07-08 16:30 | 1-High | Coding Errors | Y | Defect | 1-High |  | There is no option for filtering/searching products on the website.
10 | Cycle 1 | UN_10 | System Testing | Release 1 | 2021-07-09 | Saanya Dhir |  | 2 | UniformStore_User |  | User not being directed to website directly on login. | QA | 2021-07-08 16:30 | 1-High | Coding Errors | Y | Defect | 1-High |  | Whenever the user logins, he is directed to My Accounts page, instead of the main website homepage.
11 | Cycle 2 | UN_11 | System Testing | Release 1 | 2021-07-09 | Saanya Dhir |  | 2 | UniformStore_Admin_AddProducts |  | Price field not mandatory. | QA | 2021-07-09 17:00 | 1-Medium | Coding Errors | Y | Defect | 1-Medium |  | While adding a new product, price field is not mandatory.
12 | Cycle 2 | UN_12 | System Testing | Release 1 | 2021-07-09 | Saanya Dhir |  | 2 | UniformStore_Admin_AddProducts |  | Quantity field not mandatory. | QA | 2021-07-09 17:00 | 1-Medium | Coding Errors | Y | Defect | 1-Medium |  | While adding a new product, quantity field is not mandatory.
13 | Cycle 2 | UN_13 | System Testing | Release 1 | 2021-07-09 | Saanya Dhir |  | 2 | UniformStore_Admin_AddProducts |  | Manufacturer field not mandatory. | QA | 2021-07-09 17:00 | 1-Medium | Coding Errors | Y | Defect | 1-Medium |  | While adding a new product, manufacturer details are not mandatory.
14 | Cycle 1 | UN_14 | System Testing | Release 1 | 2021-07-09 | Shravya B C |  | 1 | Uniformstore_admin_Reports_sales_orders |  | Start Date and End Date cannot be blank | QA | 2021-07-09 11:42 | 1-High | Coding Errors | Y | Defect | 1-High |  | In orders if admin don't want to filter on the basis of dates,still dates get selected.
15 | Cycle 2 | UN_15 | System Testing | Release 1 | 2021-07-09 | Shravya B C |  | 2 | UniformStore_Admin_Reports |  | Date fields are not mandatory in tax,shipping, and return reports | QA | 2021-07-09 17:00 | 1-Medium | Coding Errors | Y | Defect | 1-Medium |  | If admin wants to display list of reports from start date to end date, selecting the date fields are not mandatory
16 | Cycle 2 | UN_16 | System Testing | Release 1 | 2021-07-09 | Shravya B C |  | 2 | UniformStore_Admin_Reports |  | Order status and Group by are mandatory in all the reports | QA | 2021-07-09 17:00 | 1-Medium | Coding Errors | Y | Defect | 1-Medium |  | If admin wants to display list of reports then its mandatory to select the group and status of order
17 | Cycle 1 | UN_17 | System Testing | Release 1 | 2021-07-09 | Soumya Hugar |  | 1 | UniformStore_admin_customers |  | No inteference for IP address field | QA | 2021-07-09 10:15 | 1-High | Coding Errors | Y | Defect | 1-High |  | No appropriate interference to add and update IP address during addition of Customers
18 | Cycle 1 | UN_18 | System Testing | Release 1 | 2021-07-09 | Soumya Hugar |  | 1 | UniformStore_admin_Customer_CustomField |  | Custom fields Section is in appropriate | QA | 2021-07-09 10:45 | 1-High | Coding Errors | Y | Defect | 1-High |  | During addition of Custom fields, one mandatory field “Custom Field Value Name” , once given the field name and edited, value name is not updated, That is, field value name has no functionalities but it is mandatory
19 | Cycle 1 | UN_19 | System Testing | Release 1 | 2021-07-09 | Soumya Hugar |  | 1 | UniformStore_admin_customer_Customfield_sortorder |  | Sort order under custom field is inappropriate | QA | 2021-07-09 10:50 | 1-High | Coding Errors | Y | Defect | 1-High |  | In Custom fields Section, during addition of new custom fields, when new sort order is edited, by default the sort order is displayed as zero, that is no updation in sort order
20 | Cycle 2 | UN_20 | System Testing | Release 1 | 2021-07-09 | Soumya Hugar |  | 1 | UNiformStore_admin_Customerlist |  | Two unused fields in Customer List | QA | 2021-07-09 04:40 | 1-medium | UI Errors | Y | Defect | 1-medium |  | Under all customer list fields, there are two unused fields , which hs no functionality and cannot be accessed.
21 | Cycle 1 | UN_21 | System Testing | Release 1 | 2021-07-09 | Sindhuja pula |  | 1 | UniformStore_AddNewOrder |  | New Order is added successfully to the system even if all the necessary information is not given and does not make any difference regarding features of the Order. | QA | 2021-07-09 11:30 | 1-Critical | Coding Errors | Y | Defect | 1-Medium |  | Before adding a Order to the system ,enough data is not provided and provided details does not reflect any changes to the qualities of order.
22 | Cycle 2 | UN_22 | System Testing | Release 1 | 2021-07-09 | Sindhuja pula |  | 1 | UniformStore_AddNewOrder |  | Shipping address details are added by default | QA | 2021-07-09 11:30 | 1- Critical | Coding Errors | Y | Defect | 1-Medium |  | to interfrence to add the shipping details
23 | Cycle 1 | UN_23 | System Testing | Release 1 | 2021-07-09 | Sindhuja pula |  | 1 | UniformStore_Delete Existing Order |  | Existing order has to be deleted by giving order details | QA | 2021-07-09 11:30 | 1-Critical | Coding Errors | Y | Defect | 1-Medium |  | Before deleting a Order to the system ,enough data is not provided and details are not given and does not reflect any changes to the qualities of order.
24 | Cycle 2 | UN_24 | System Testing | Release 1 | 2021-07-09 | Sindhuja pula |  | 1 | UniformStore_Delete Existing Order |  | Recurring ID has to be applied for delete on order | QA | 2021-07-09 11:30 | 1- Critical | Coding Errors | Y | Defect | 1-Medium |  | For an Delete an order,Recurring Id has to be given for the existing order and it has not provided.
25 | Cycle 1 | UN_25 | System Testing | Release 1 | 2021-07-09 | Sindhuja pula |  | 1 | UniformStore_Update Order |  | Existing order has to be update by giving order details by using Order ID | QA | 2021-07-09 11:30 | 1-Critical | Coding Errors | Y | Defect | 1-Medium |  | Before Updating a Order to the system ,enough data is not provided and Order ID is not given and does not reflect any changes to the order.
26 | Cycle 2 | UN_26 | System Testing | Release 1 | 2021-07-09 | Sindhuja pula |  | 2 | UniformStore_Admin_AddOrder |  | Product field should be mandatory. | QA | 2021-07-09 17:00 | 1-Medium | Coding Errors | Y | Defect | 1-Medium |  | While adding a new product, product field should be mandatory.
27 | Cycle 2 | UN_27 | System Testing | Release 1 | 2021-07-09 | Sindhuja pula |  | 2 | UniformStore_Admin_AddOrder |  | Quantity of Product field should be mandatory. | QA | 2021-07-09 17:00 | 1-Medium | Coding Errors | Y | Defect | 1-Medium |  | while adding a product,quantity of the product should be mandatory
28 | Cycle 2 | UN_28 | System Testing | Release 1 | 2021-07-09 | Sindhuja pula |  | 2 | UniformStore_Admin_AddOrder |  | Address field should be mandatory. | QA | 2021-07-09 17:00 | 1-Medium | Coding Errors | Y | Defect | 1-Medium |  | While ordering a product,Address field should be mandatory.
29 | Cycle 1 | UN_29 | System Testing | Release 1 | 2021-07-09 | Rohini |  | 2 | UniformStore_AddNewManufacturer |  | Repeated addition of manufacturer is allowed with incompletely filled details | QA | 2021-07-09 11:30 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Duplication of manufacturer is possible when SEO URL field is not filled.
30 | Cycle 1 | UN_30 | System Testing | Release 1 | 2021-07-09 | Rohini |  | 2 | UniformStore_AddNewManufacturer |  | Sort order field does not really order the list as provided | QA | 2021-07-09 11:30 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Sorting doesn’t take place even after specifying the sort order.
33 | Cycle 1 | UN_33 | System Testing | Release 1 | 2021-07-09 | Rohini |  | 2 | UniformStore_UpdateManufacturerDetails |  | Sort order field does not really order the list as provided | QA | 2021-07-09 12:27 | 1-Critical | Coding Errors | Y | Defect | 1-Critical |  | Sorting doesn’t take place even after specifying the sort order.
34 | Cycle 2 | UN_34 | System Testing | Release 1 | 2021-07-09 | Rohini |  | 2 | UniformStore_AddNewManufacturer |  | SEO URL field should be mandatory as it holds the unique value with respect to manufacturer identity. | QA | 2021-07-09 10:56 | 3-Medium | Coding Errors | Y | Defect | 3-Medium |  | SEO URL field should be made mandatory.
35 | Cycle 1 | UN_35 | System Testing | Release 1 | 2021-07-09 | Sivaranjani |  | 2 | UniformStore_AddOption |  | Option value name is inappropriate | QA | 2021-07-09 11:30 | High | Coding Errors | Y | Defect | High | Closed | once the new Options are added to the lists, the Option name is visible whereas the value name is not as it is a required field
36 | Cycle 1 | UN_36 | System Testing | Release 1 | 2021-07-09 | Sivaranjani |  | 2 | UniformStore_AddOption |  | Sort Order under Option values is not suitable | QA | 2021-07-09 11:30 | High | Coding Errors | Y | Defect | High | Closed | During the addition of new Options, there are 2 Sort order fields to be filled,
37 | Cycle 2 | UN_37 | System Testing | Release | 2021-07-09 | Sivaranjani |  | 2 | UniformStore_Admin_Options |  | Type field should be mandatory | QA |  | Medium | Coding Errors | Y | Defect | medium | Closed | While adding the new options, the type should be made mandatory
38 | Cycle 2 | UN_38 | System Testing | Release | 2021-07-09 | Sivaranjani |  | 2 | UniformStore_Admin_Options |  | Date, time and file under type field is not necessary | QA |  | Medium | Coding Errors | Y | Defect | medium | Closed | date, time and files are not needed under type field in measurement units.
39 | Cycle 1 | UN_39 | System Testing | Release 1 | 2021-07-09 | Ramya C |  | 2 | UniformStore_Admin_UpdateCategory |  | Sort order field does not really order the list as provided | QA | 2021-07-09 12:30 | 1-High | Coding Errors | Y | Defect | 1-High |  | Sorting doesn’t take place even after specifying the sort order.
40 | Cycle 2 | UN_40 | System Testing | Release 1 | 2021-07-09 | Ramya C |  | 2 | UniformStore_Admin_AddCategory |  | Meta tag title field is mandatory. | QA | 2021-07-09 17:45 | 3-Medium | Coding Errors | Y | Defect | 3-Medium |  | While adding a new category, meta tag title field is mandatory.
41 | Cycle 2 | UN_41 | System Testing | Release 1 | 2021-07-09 | Ramya C |  | 2 | UniformStore_Admin_AddCategory |  | Sort order field is not mandatory. | QA | 2021-07-09 17:45 | 3-Medium | Coding Errors | Y | Defect | 3-Medium |  | While adding a new category, Sort order field is not mandatory.